## Dev Tracker
Area | Task | Status | Priority | Notes
Brand & Homepage | Apply Kapruka brand colors (purple #3C096C / gold) and Inter font site-wide | Done
Brand & Homepage | Rebuild homepage to wireframe (hero, category pills, popular services, footer) | Done
Brand & Homepage | Hero background video with legible text overlay | Done
Brand & Homepage | Hero H1 copy: 'Get expert marketing without the agency cost.' | Done
Brand & Homepage | 'Powered by Kapruka' in header + footer | Done
Brand & Homepage | Remove packages ladder + duplicate services grid from homepage | Done
Services & Gig Pages | /services listing page for all 9 services | Done
Services & Gig Pages | /services/[slug] gig page per wireframe (breadcrumb, gallery, description, sidebar, tabs) | Done
Services & Gig Pages | Reviews tab honest empty state (no fake reviews/logos/personas) | Done
Services & Gig Pages | Uniform token pricing: Basic 50 / Standard 200 / Premium 500 tokens/mo | Done
Services & Gig Pages | Real package copy — SEO (Basic + Standard) | Done
Services & Gig Pages | Real package copy — GEO (Basic + Standard) | Done
Services & Gig Pages | Confirm real package copy — CRO | Pending | Medium | Currently placeholder features/delivery days/revisions
Services & Gig Pages | Confirm real package copy — Google Ads | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — Meta Ads | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — Content Strategy | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — Video Creation | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — Graphic Design | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — Video Editing | Pending | Medium | Currently placeholder
Services & Gig Pages | Confirm real package copy — GEO Premium tier | Pending | Medium | Basic/Standard are real, Premium is still placeholder
Accounts & Ordering | Signup/login required before ordering | Done
Accounts & Ordering | Atomic checkout — token deduction + duplicate-active-order guard | Done
Accounts & Ordering | Thank-you page with live countdown to delivery deadline | Done
Accounts & Ordering | 'Purchase activity' in customer dashboard (orders + downloads) | Done
Admin Backend | Role-based admin access (DB role field, not hardcoded emails) | Done
Admin Backend | /admin — all businesses' orders, services, deadlines, statuses | Done
Admin Backend | Per-order detail page + file-upload delivery | Done
Admin Backend | Customer download endpoint (owner/admin gated, post-delivery only) | Done
Admin Backend | Separate admin login credentials created | Done
Admin Backend | Fix: admin login falling into customer onboarding/client view | Done
Cleanup | Remove legacy /dashboard/[expert] audit-tool system entirely | Done
Cleanup | Write PRODUCT-BRIEF.md for copywriters | Done
Payments | Real payment gateway for token top-up | Pending | High | Wallet currently credits tokens instantly with no real payment step
Payments | Refund flow / UI (ORDER_REFUND reason exists in schema, unused) | Pending | Low
Order Lifecycle | Email notifications (order placed, delivered, deadline approaching) | Pending | Medium
Order Lifecycle | Auto-resume checkout after guest signup/onboarding detour | Pending | Low | User currently has to manually re-click Continue
Order Lifecycle | Cancellation flow for a pending order | Pending | Low
Account | Password-reset flow | Pending | Medium
Open Questions | Confirm scope of 'remove analyzing brand kit' | Pending | High | Routing fix may fully cover it, or it may mean removing 'Putting together your brand kit' onboarding loading-stage copy
Open Questions | Clarify 'two of them have mixed create separate lines' | Pending | High | No screenshot/context ever received — need more detail
Polish / Housekeeping | Drop unused legacy Audit/Finding/Expert/Package Prisma models | Pending | Low | Harmless to leave, future cleanup migration
Polish / Housekeeping | Automated tests (unit/e2e) | Pending | Medium | QA so far has been manual, throwaway Playwright scripts
Polish / Housekeeping | Re-verify mobile viewport after order-flow changes | Pending | Medium
Polish / Housekeeping | Privacy policy / terms / refund policy pages | Pending | High | Likely needed before real payments go live

## Summary
Metric | Count
Total tasks | 44
Done | 24
Pending | 20
% complete | 55%